## Slide 1
Digital Banking Platform Upgrade
Steering Committee Update — Month 8 of 12 | PRJ-2026-0147
Prepared by Keshaav Gite | Project Control Officer, PMP · CSM
Illustrative sample deck built from a self-directed portfolio project (fictional client: Northbridge Financial Group) — for demonstration of reporting style only.

## Slide 2
Project Overview
Budget (BAC)
$1.26M
Contingency
5.4%
Timeline
Month 8 / 12
Overall RAG
AMBER
Objective
Upgrade Northbridge's retail digital banking platform to an API-first architecture — enabling real-time payments, cutting the release cycle from 12 weeks to 2 weeks, and closing the gap to OSFI B-13 technology-risk expectations.
My Role
Project Control Officer — schedule, cost, RAID, and reporting.
Toolchain
MS Project WBS, dependencies, 6 milestones, baseline
Dynamics 365 Vendor POs & invoices — source of actuals
Excel RAID, change control, EAC cost model
Power BI Interactive steering pack

## Slide 3
Cost Performance — Estimate at Completion (EAC)
Chart: $ CAD
| BAC (Budget) | Actual to Date | Committed POs | ETC | Forecast (EAC)
Amount ($) | 1260000 | 720000 | 214600 | 296861 | 1291461
The Story
YTD spend was dead on plan — 0.1% variance. Reporting Green on this alone would have been easy, and misleading.
Adding $214,600 of committed POs, the forecast lands $31,461 OVER budget.
Flagged a full quarter early as AMBER — turning a hidden overrun into a planned contingency drawdown instead of a year-end emergency.
Figures from self-directed portfolio project — for demonstration purposes only.

## Slide 4
AP Data Review — Findings
Finding | Impact | Status
Duplicate invoice identified in AP export | High | Resolved
Invoice missing PO reference (policy breach) | High | Escalated
$28K of unposted invoices understating the month | Medium | Corrected
USD invoice requiring currency conversion | Low | Resolved
Contractor Labour category running 22% over plan | High | Under Review
Why it matters:
Each finding was caught through formula-driven reconciliation of the AP export against committed POs — not manual spot-checking. This is what surfaced the true forecast position a quarter ahead of year-end.
Illustrative sample entries — for demonstration purposes only.

## Slide 5
RAID & Change Control Snapshot
RAID Items
12
Change Requests
6 (1 rejected)
Actions Open
8
Decisions Logged
5
Key Items
All 12 RAID items originated from real reconciliation findings — not assumptions.
Contractor rate renegotiation triggered as a direct result of cost variance escalation.
1 change request rejected at governance review — scope held firm against schedule pressure.
Milestone tracker maintained baseline vs. forecast vs. actual for all 6 project milestones.
Prepared by Keshaav Gite | Project Control Officer

## Slide 6
Recommendation & The Ask
Overall Status: AMBER
Forecast at completion is $31,461 over the $1.26M budget — driven by committed POs and a 22% overrun in Contractor Labour. Contingency (5.4%) covers the gap; no schedule impact expected.
The Ask
Approve drawdown of contingency to absorb the $31,461 forecast overrun.
Endorse the Contractor Labour rate renegotiation already in progress.
No change to go-live timeline or OSFI B-13 milestone commitments.
Next Reporting Cycle
Month 9 update will confirm renegotiated contractor rate impact and updated EAC.
Illustrative sample deck — for demonstration purposes only.