## Slide 1
Portfolio Governance & Resource Capacity
Portfolio Steering Review | PRJ-2026-0212
Prepared by Keshaav Gite | Project Control Officer, PMP · CSM
Illustrative sample deck built from a self-directed portfolio project (fictional client: Meridian Digital Consulting) — for demonstration of reporting style only.

## Slide 2
Portfolio Overview
Portfolio Revenue
$2.215M
Cost Budget
$1.640M
Projects
6
Shared Bench
15 people
Driver
Resourcing scattered across disconnected spreadsheets — no visibility into over/under-allocation, and PM self-reported RAG was masking real budget exposure.
Objective
One connected capacity & governance model — RAG computed independently of PM self-reporting, hidden capacity recovered, over-allocation visible weekly.
Toolchain
MS Project 25-task schedule, baselined, live variance
Excel 17-tab connected model feeding two dashboards
Power BI Portfolio & utilisation analytics — in development
Power Automate Booking-chaser flow — in development

## Slide 3
Utilisation & Margin — The Hidden Picture
Chart: %
| Portfolio Avg. Utilisation | Senior Dev (peak, 3 wks) | Margin at Start | Margin After Committed Costs
% | 86 | 140 | 26 | 15.6
The Story
86% average utilisation looked healthy — it hid a senior developer booked at 140% for 3 straight weeks across two fixed-price go-lives.
A part-time analyst was booked past contracted hours; six data defects were masking real capacity.
Margin was eroding 26.0% → 15.6% once committed costs were counted — invisible in PM self-reported status alone.
Figures from self-directed portfolio project — for demonstration purposes only.

## Slide 4
Data Integrity — 12 Defects Found
Defect | Impact | Status
Ghost resource — booked but not on active roster | High | Removed
Duplicate & blank bookings across allocations export | Medium | Cleared
~60 hours of phantom “tentative” holds | Medium | Released
Contract breach — capped part-time role over hours | High | Escalated
Committed costs understating 3 of 6 projects | High | Corrected
Why it matters:
All 12 defects were caught by formula-driven reconciliation across the 17-tab model — not guessed. This is what allowed the computed RAG to catch what PM self-reporting missed.
Illustrative sample entries — for demonstration purposes only.

## Slide 5
Computed RAG vs. PM-Reported RAG
Projects Reviewed
6
Under-Reported
3 of 6
Unplanned Cost Surfaced
$228,477
Hidden Capacity Recovered
~60 hrs
Key Finding
3 of 6 projects flagged UNDER-REPORTED — computed Amber/Red against a PM-reported Green.
Computed RAG used Actual + Committed + Remaining Budget against documented variance thresholds, independent of self-reporting.
An 86% average utilisation and a mostly-Green portfolio were both technically true, and both hiding the real picture.
Prepared by Keshaav Gite | Project Control Officer

## Slide 6
Recommendation & The Ask
Actions Already Taken
Rebalanced the over-allocated developer, held the part-timer to contract, and cleared data defects to recover approximately 60 hours of hidden capacity.
The Ask
Endorse the computed RAG model as the standing governance view going forward, alongside PM self-reporting.
Approve continued weekly over-allocation monitoring via the capacity dashboard.
Sponsor completion of the Power BI and Power Automate layers to automate the booking-chaser workflow.
Next Reporting Cycle
Confirm margin recovery across the 3 flagged projects and validate the booking-chaser automation pilot.
Illustrative sample deck — for demonstration purposes only.